## Slide 1: How To
Collaborate as a Team

## Slide 2: Why Team Projects Fail
No clear division of responsibilities
Team members assume someone else is doing the work
Poor communication
Work starts too late
One person does most of the work
Conflicts are ignored until the deadline approaches
No system for tracking progress

## Slide 3: Step 1: Define the Project
Discuss:
  What does success look like?
  What are the required deliverables?
  What are the grading criteria?
  What are the major milestones?
Create a shared project summary that includes everything spelled out including communication methods, project summary with deadlines and anything else that the team thinks is important to bring up

## Slide 4: Step 2: Establish Team Expectations
Communication
  How will we communicate?
  How quickly should messages be answered?
  What happens if someone is unavailable?
Meetings
  How often will we meet?
  In person or online?
  Who schedules meetings?
Accountability
  What happens if a deadline is missed?
  How will concerns be raised?
  How will work be reviewed before submission?

## Slide 5: Step 3: Break Work Into Tasks
Avoid agreeing to vague responsibilities
Tasks should be:
  Specific
  Measurable
  Assigned to specific people
  Time-bound

## Slide 6: Step 4: Create Internal Deadlines
Never use the final due date as the first deadline
Internal deadlines create room for revisions and unexpected problems
Plan for issues and roadblocks
Make sure to take into account everyone's schedule and availability
  For example, if you have things do in 3 classes on one day that might not be a good day to have more things due

## Slide 7: Step 5: Track Progress
Teams should always know:
  What is complete
  What is in progress
  What still needs to be done
  Who is working on what
Tool Ideas/Suggestions:
  Trello
  GitHub Projects
  Microsoft Planner
  Sticky notes
  Whiteboard

## Slide 8: Step 6: Address Problems Early
Most team conflicts become difficult because nobody addresses them
Clear and straightforward communication is important
Remember everyone wants to do well and thinks they are a good person; conflicts can come from misunderstandings and communication issues
Focus on: | Avoid:
Actions | Personal attacks
Expectations | Assumptions
Solutions | Public confrontation

## Slide 9: Example: Research Presentation Team
Assignment: Create a 15-minute presentation on renewable energy policy
Team: 4 students
Things to do:
  Topic selection
  Research
  Content development
  Slide creation
  Presentation preparation

## Slide 10: Example – Research Phase
Research Phase: Each student finds 2–3 credible sources and does some research on the topic independently
As a group Discuss:
  Evaluate source quality
  Compare findings
  Identify common themes
  Decide which information to include

## Slide 11: Example – Start the project
Content Development:
  Create presentation outline together
  Determine and list key points
  Decide who will explain each section
Slide Development could be done together or independently for each section

## Slide 12: Example - Practice and Revision
Review visual design, slides and citations
Suggest improvements and practice
Practice presentation
Time each section
Identify unclear explanations
Revise if needed!

## Slide 13: Example – Check-ins and what's a success
Check-In 1
  Are the sources credible and relevant?
Check-In 2
  Does the presentation address all assignment requirements?
Check-In 3
  Can every team member explain the project and answer questions?
Success Factors
  Shared understanding of the topic
  Regular meetings
  Collective review of all materials
  Everyone participates throughout the project